## Harish
Project Title: Abstractive Text Summarization with OpenAI: Developing an Interactive Web Application for summarizing medical documents.
Project Start Date : 26-June-2023 Project End Date : 18-September-2023 Developer Name : Harish Ahamed Samsugani Babu Total Days : 85
|  |  |  | JUNE |  |  |  |  | JULY | [30 empty] | AUGUST | [30 empty] | SEPTEMBER
|  |  |  | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Milestone description | Category | Start | Days
CMP7200 Master's Project |  | 2023-06-26 | 85
Business Understanding | Learning | 2023-06-26 | 7 | bar: JUNE 26 to JULY 2
Techinical and Non-Technical Understanding | Learning | 2023-06-26 | 4 | bar: JUNE 26 to JUNE 29
Collecting Resource | Learning | 2023-06-26 | 3 | bar: JUNE 26 to JUNE 28
Data Collection & Acquisition | Development | 2023-06-27 | 7 | bar: JUNE 27 to JULY 3
Data Preparation | Development | 2023-06-27 | 2 | bar: JUNE 27 to JUNE 28
Modeling | Development | 2023-06-28 | 65 | bar: JUNE 28 to AUGUST 31
Model Selection & API | Development | 2023-06-28 | 18 | bar: JUNE 28 to JULY 15
Development of Front-End & Back-End | Development | 2023-06-28 | 65 | bar: JUNE 28 to AUGUST 31
Model Evaluation | Development | 2023-08-15 | 23 | bar: AUGUST 15 to AUGUST 31
Depployment | Development | 2023-08-15 | 23 | bar: AUGUST 15 to AUGUST 31
Documentation | Writing | 2023-09-01 | 17 | bar: SEPTEMBER 1 to SEPTEMBER 17
Viva | Voice | 2023-09-01 | 18 | bar: SEPTEMBER 1 to SEPTEMBER 18